## Current project plan
Task | Description | Start Date | End Date | Status
Database
| server setup | 2014-01-01 | 2014-01-05 | complete
| install database | 2013-01-04 | 2014-01-05 | complete
| scripts to create user tables | 2014-01-05 | 2014-02-08 | complete
| function to add user | 2014-01-05 | 2014-02-08 | complete
| function to update user password | 2014-02-08 | 2014-02-08 | complete
| function to update user rating | 2014-02-08 | 2014-02-08 | complete
| function to update user status | 2014-02-08 | 2014-02-08 | complete
| function to log user on | 2014-02-08 | 2014-02-08 | complete
| function to log user off | 2014-02-08 | 2014-02-08 | complete
| scripts to create page tables | 2014-02-09 | 2014-02-15 | on target
| function to create page | 2014-02-09 | 2014-02-15 | on target
| function to update page | 2014-02-09 | 2014-02-15 | on target
| function to delete page | 2014-02-09 | 2014-02-15 | on target
| function to change page rating | 2014-02-09 | 2014-02-15 | on target
| scripts to create user tag table | 2014-02-16 | 2014-02-22 | on target
| function to add user tag | 2014-02-16 | 2014-02-22 | on target
| function to update user tag | 2014-02-16 | 2014-02-22 | on target
| function to delete user tag | 2014-02-16 | 2014-02-22 | on target
| Script to reset data for multiple tests | 2014-02-16 | 2014-02-22 | on target
| Versioning scripts for table/function creation | 2014-02-23 | 2014-03-01 | on target
Go
| install go on server | 2014-01-01 | 2014-01-28 | complete
| set up drivers for Go to user postgres | 2014-01-01 | 2014-02-15 | potentially in trouble
| verification program of go accessing postgres on server | 2014-02-08 | 2014-02-15 | potentially in trouble
| code for user functions | 2014-02-16 | 2014-02-22 | potentially in trouble
| test program to for user functions with verified results | 2014-02-16 | 2014-02-22 | potentially in trouble
| code for page functions | 2014-02-23 | 2014-03-01 | potentially in trouble
| test program to for page functions with verified results | 2014-02-23 | 2014-03-01 | potentially in trouble